# CFIP Implementation Roadmap

20-Week Development Plan

# Phase 1: Foundation (Weeks 1-4)

Goal: Build core infrastructure and basic functionality

## Week 1: Project Setup

- Initialize Git repository and set up development environment

- Install Node.js, PostgreSQL, Redis, and Docker

- Create React frontend boilerplate with TypeScript

- Set up Express.js backend with GraphQL

- Configure ESLint, Prettier, and testing frameworks

## Week 2: Database & Authentication

- Design and implement database schema

- Create migration scripts for all tables

- Implement JWT-based authentication

- Build user registration and login pages

- Add password hashing and validation

## Week 3: Basic Calculator

- Import emission factor data from EPA and IPCC

- Implement core calculation logic

- Create calculator input form UI

- Display calculation results

- Write unit tests for calculation functions

## Week 4: Simple Dashboard

- Create main dashboard layout

- Display key metrics (total emissions, recent calculations)

- Add simple line chart for emission trends

- Implement navigation menu

- Deploy Phase 1 to ICU dev server for testing

# Phase 2: Core Features (Weeks 5-9)

Goal: Add advanced features and visualizations

## Week 5: Advanced Calculator

- Add support for multiple shipments at once

- Implement CSV import for bulk calculations

- Add adjustment factors (weather, traffic, load)

- Support for Scope 1, 2, and 3 emissions

- Create calculation history and search

## Week 6: Data Visualization

- Integrate Recharts library

- Build emissions by category pie chart

- Create emissions over time line chart with zoom

- Add emissions by transport mode bar chart

- Implement interactive tooltips and filters

## Week 7-8: Goal Tracking Module

- Build goal creation form (reduction %, absolute targets)

- Implement progress tracking against goals

- Add milestone notification system

- Create goal dashboard with progress bars

- Support for multiple concurrent goals

- Goal comparison with industry benchmarks

## Week 9: Reporting Module

- Build custom report builder interface

- Implement PDF generation with charts

- Add Excel export functionality

- Create CDP-compliant report template

- Test Phase 2 features with sample data

# Phase 3: AI & Optimization (Weeks 10-13)

Goal: Add predictive analytics and optimization engine

## Week 10: ML Infrastructure

- Set up Python microservice for ML

- Install TensorFlow and scikit-learn

- Create data pipeline for model training

- Generate synthetic training data (if real data insufficient)

- Build API endpoints for ML service

## Week 11: Predictive Model

- Train XGBoost model for emission prediction

- Validate model accuracy (target: ±10%)

- Implement prediction confidence intervals

- Create prediction UI in frontend

- Add prediction vs actual comparison

## Week 12: Optimization Engine

- Implement optimization algorithm

- Generate alternative route suggestions

- Calculate emission savings for each option

- Build optimization dashboard panel

- Add one-click implementation of suggestions

## Week 13: What-If Scenarios & Anomalies

- Build scenario comparison tool

- Implement side-by-side scenario analysis

- Train anomaly detection model

- Add real-time anomaly alerts

- Test all AI features thoroughly

# Phase 4: Integration & Collaboration (Weeks 14-17)

Goal: Connect with external systems and enable collaboration

## Week 14: RESTful API Development

- Design comprehensive REST API

- Implement all endpoints (see Technical Specs)

- Add API authentication (API keys)

- Write API documentation with Swagger

- Test API with Postman

## Week 15: ERP Integration

- Build generic ERP connector framework

- Create sample SAP connector (demo)

- Implement automatic data sync

- Add integration settings page

- Test with mock ERP data

## Week 16: Blockchain Implementation

- Set up Hyperledger Fabric test network

- Create smart contracts for carbon verification

- Implement blockchain logging for key operations

- Add verification UI showing blockchain proof

- Test immutability and audit trail

## Week 17: Stakeholder Portal

- Create supplier portal with data entry forms

- Build carrier portal for transportation data

- Implement customer-facing carbon dashboard

- Add collaboration features (comments, notifications)

- Test multi-user workflows

# Phase 5: Testing & Deployment (Weeks 18-20)

Goal: Ensure quality and deploy to production

## Week 18: Beta Testing

- Recruit 15-20 beta testers (supply chain managers)

- Conduct usability testing sessions

- Gather feedback through surveys

- Measure task completion rates

- Fix critical bugs and issues

## Week 19: Refinement & Documentation

- Incorporate user feedback

- Polish UI/UX based on testing

- Write user documentation and help guides

- Create video tutorials for key features

- Finalize technical documentation

## Week 20: Production Deployment

- Set up production environment on ICU servers

- Configure SSL certificates and domain

- Deploy application to production

- Set up monitoring and alerts

- Configure automated backups

- Conduct final smoke tests

- Launch CFIP to users!

# Success Metrics

Track these KPIs to measure project success:

| Metric | Target |
| --- | --- |
| Calculation Accuracy | ±5% vs manual calculations |
| Prediction Accuracy | ±10% for emission forecasts |
| User Adoption | 50+ active users in first 3 months |
| Task Completion Rate | >90% for core workflows |
| System Performance | <2 sec page load, 99.5% uptime |
| User Satisfaction | 4.5/5 average rating |
| Emission Reductions Enabled | 15-30% through optimizations |

# Risk Mitigation

| Risk | Probability | Mitigation |
| --- | --- | --- |
| Insufficient training data for ML | Medium | Use synthetic data generation + transfer learning |
| Scope creep delaying delivery | High | Strict adherence to MVP features, defer nice-to-haves |
| Technical challenges with blockchain | Medium | Start simple, add complexity gradually |
| Low user adoption | Low | Focus on usability, provide training, gather feedback early |
| Server/hosting issues | Low | Work closely with ICU IT, have backup plans |

# Quick Start Checklist

Use this checklist to begin immediately:

- Review all three documents (Proposal, Technical Specs, Roadmap)

- Set up meeting with supervisor to discuss approach

- Install development tools (Node.js, PostgreSQL, Docker, VS Code)

- Create GitHub repository for version control

- Download emission factor datasets from EPA and IPCC

- Set up project management board (Trello/Jira/GitHub Projects)

- Schedule weekly progress reviews with supervisor

- Start Week 1 tasks: project setup and environment configuration

You're ready to build something amazing!

— End of Roadmap —